## Slide 1: Scrum

## Slide 2: What is Scrum?
Scrum is an agile software development framework
  An iterative, incremental framework for developing any product or managing any work
  It allows teams to deliver set of product functions every iteration which respond to changing requirements

## Slide 3: Scrum Terms
Sprint
  Basic unit of development
  Usually lasts between one week to one month
  Sprint length is determined by team
User stories
  Customer requirements
  Include list of high-level features and priorities for each features

## Slide 4: Scrum Terms
Product backlog
  High-level document for entire project
  Contains descriptions of required features
  Should be prioritized by the product owner

## Slide 5: Scrum Terms
Sprint backlog
  Property of the team
  Contains information regarding how team will implement of features for a sprint
  Contains breakdown of tasks
  Tasks on backlog are not assigned
    Rather team members sign up for tasks as needed
    Who performs the task will depend upon team skills and priorities

## Slide 6: Scrum Sprint Backlog

## Slide 7: Scrum Terms
Task board
  Used to display the status of various tasks during a sprint
  Each row on a task board contains a user story
  Status might be posted as “done”, “in progress”, “to do”

## Slide 8: Scrum Task Board
Image from: http://www.mountaingoatsoftware.com/task-boards

## Slide 9: Scrum Terms
Burn down chart
  Graphical representation of what work is left to do versus time
  Vertical axis is the backlog (work left to do)
  Horizontal axis is time

## Slide 10: Scrum Burn Down Chart
Image from: http://en.wikipedia.org/wiki/File:SampleBurndownChart.png

## Slide 11: Scrum Roles
Product Owner
  Spokesperson for stakeholders
  Define and prioritize product features
ScrumMaster
  Like a project manager
  Maintains the processes
  Responsible for following Scrum practices

## Slide 12: Scrum Roles
Team
  Cross-functional group of up to 7 people
  Perform actual analysis, design, programming, implementation, testing, etc.
  Teams are self-organizing
Scrum Team
  Product Owner, ScrumMaster, Team

## Slide 13: Other Roles
Stakeholders
  Customers, vendors, etc.
Management
  People within the company that set up the product environment
Stakeholder and management are not part of the Scrum team

## Slide 14: Sprint Planning Meeting
Sprint planning is completed by ScrumMaster and Team
Analyze the product backlog
Determine and select what tasks to include in sprint backlog
Determine and assign hours to complete a task for sprint backlog
Usually an eight hour limit for this meeting

## Slide 15: Daily Scrum
Daily meeting usually up to 15 minutes
Usually meant to be a “stand-up” only meeting
Meeting location is usually at the same location and time every day
  Often in the morning
Only ScrumMaster, Team and Product Owner are welcome

## Slide 16: Daily Scrum
Daily Scrum questions
  What have you accomplished since yesterday?
  What are you planning to do today?
  Are there any problems that are preventing you from finishing your goal today?
Answers to these questions are meant to commit team members to certain work in front of team

## Slide 17: Sprint Review
Usually two to four hour limit for sprint review
Team presents demo to stakeholder showing features
Review work completed
Discuss work not completed
  No incomplete work will be demonstrated to stakeholder

## Slide 18: Sprint Retrospective
Usually attended by ScrumMaster, Team, Product Owner and sometimes stakeholders
Completed after every sprint
Typically lasts 15 to 30 minutes but may last up to 3 hours
Discuss what went well in sprint
Discuss what could be improved for next sprint

## Slide 19: Scrum Characteristics
Scrum goal is to deliver a quality product
Self-organizing small teams
Series of sprints make up the product progress
Product backlog contains items in list which captures requirements

## Slide 20: Scrum Characteristics
Good framework for changing customer requirements
Interactions and communication between team are improved by Scrum framework
Must have a client that knows what they want
  Also needs someone to commit to become part of the Scrum team

## Slide 21: Scrum Versus Waterfall
Taken from: http://www.scrumalliance.org/articles/133-challenging-inertia-through-scrum

## Slide 22: Scrum Criticisms
Scrum may fall apart if politics enter the arena or if teams do not function well

## Slide 23: Scrum Resources
http://www.scrumalliance.org/
http://www.mountaingoatsoftware.com/scrum

## Slide 24: Scrum