## Slide 1: Chapter 3: The Project Management Process Groups
Information Technology Project Management, Ninth Edition
Note: See the text itself for full citations

## Slide 2: Learning Objectives (1 of 2)
Describe the five project management process groups, the typical level of activity for each, and the interactions among them
Relate the project management process groups to the project management knowledge areas
Discuss how organizations develop information technology (IT) project management methodologies to meet their needs
Review a case study of an organization applying the project management process groups to manage an IT project, describe outputs of each process group, and understand the contribution that effective initiating, planning, executing, monitoring and controlling, and closing make to project success

## Slide 3: Learning Objectives (2 of 2)
Review a case study of the same project managed with an agile focus and compare the key differences between an agile approach and a predictive approach
Describe several templates for creating documents for each process group

## Slide 4: Introduction and Project Management Process Groups
Project management consists of 10 knowledge areas
  Integration, scope, schedule, cost, quality, resource, communications, risk, procurement, and stakeholder management
Projects involve five project management process groups
  Initiating, planning, executing, monitoring and controlling, and closing
    Tailoring these process groups to meet individual project needs increases the chance of success in managing projects
A process is a series of actions directed toward a particular result
  Project management can be viewed as a number of related processes
Project management process groups
  Initiating processes
  Planning processes
  Executing processes
  Monitoring and controlling processes
  Closing processes

## Slide 5: Project Management Process Groups

## Slide 6: Media Snapshot
Just as information technology projects need to follow the project management process groups, so do other projects, such as the production of a movie
  Processes involved in making movies include screenwriting (initiating), producing (planning), acting and directing (executing), editing (monitoring and controlling), and releasing the movie to theaters (closing)
  Many people enjoy watching the extra features on a DVD that describe how these processes lead to the creation of a movie
  This acted “…not as promotional filler but as a serious and meticulously detailed examination of the entire filmmaking process.”*
  Project managers in any field know how important it is to follow a good process
*Jacks, Brian, “Lord of the Rings: The Two Towers Extended Edition (New Line)”, Underground Online (accessed from www.ugo.com August 4, 2004).

## Slide 7: Mapping the Process Groups to the Knowledge Areas
You can map the main activities of each PM process group into the ten knowledge areas using the PMBOK® Guide, Sixth Edition
  Note that there are activities from each knowledge area under the planning process groups
  Table 3-1 provides a big-picture view of the relationships among the 49 project management activities, the process groups in which they are typically completed, and the knowledge areas into which they fit

## Slide 8: Developing an IT Project Management Methodology
Many organizations develop their own internal IT project management methodologies
  A methodology describes how things should be done
  A standard describes what should be done
Different project management methodologies
  PRojects IN Controlled Environments (PRINCE2)
  Agile
  Rational Unified Process (RUP)
  Six Sigma

## Slide 9: Global Issues
In 2018 PMI published their tenth annual global project management survey (Pulse of the Profession®)
  47 percent of projects completed in organizations in the past year used a predictive approach, 23 percent used agile, 23 percent used a hybrid of predictive and agile, and seven percent used other approaches
A 2017 global survey conducted by VersionOne found that 94 percent of respondents said their organizations practiced agile, but 60 percent of their teams were not yet practicing it
  The top three benefits of agile listed were the ability to manage changing priorities, increased team productivity, and improved project visibility

## Slide 10: Project Pre-Initiation and Initiation
Initiating includes recognizing and starting a new project
  Right kinds of projects for the right reasons
Strategic planning should serve as the foundation for deciding which projects to pursue
  Expresses the vision, mission, goals, objectives, and strategies of the organization
  Provides the basis for IT project planning

## Slide 11: Pre-initiation Tasks
It is good practice to lay the groundwork for a project before it officially starts
Senior managers often perform several pre-initiation tasks
  Determine the scope, time, and cost constraints for the project
  Identify the project sponsor
  Select the project manager
  Develop a business case for a project
  Meet with the project manager to review the process and expectations for managing the project
  Determine if the project should be divided into two or more smaller projects

## Slide 12: Initiating (1 of 5)
Knowledge Area | Initiating Process | Initiating Process
Project Integration Management | Develop project charter | Project charter Assumption log
Project Stakeholder Management | Identify stakeholders | Stakeholder register Change requests Project management plan updates Project documents updates
Source: PMBOK® Guide – Sixth Edition, 2017
Table 3-3 Project initiation knowledge areas, processes,
and outputs

## Slide 13: Initiating (2 of 5)
Name | Position | Internal/External | Project Role | Contact Information
Joe Fleming | CEO | Internal | Sponsor | joe_fleming@jwdconsulting.com
Erica Bell | PMO Director | Internal | Project Manager | erica_bell@jwdconsulting.com
Michael Chen | Senior Consultant | Internal | Team Member | michael_chen@jwdconsulting.com
Kim Phuong | Business Analyst | External | Advisor | kim_phuong@client1.com
Louise Mills | PR Director | Internal | Advisor | louise_mills@jwdconsulting.com
Table 3-4 Stakeholder Register

## Slide 14: Initiating (3 of 5)
Name | Level of Interest | Level of Influence | Potential Management Strategies
Joe Fleming | High | High | Joe likes to stay on top of key projects and make money. Have a lot of short, face-to-face meetings and focus on achieving the financial benefits of the project.
Louise Mills | Low | High | Louise has a lot of things on her plate, and she does not seem excited about this project. She may be looking at other job opportunities. Show her how this project will help the company and her resume.
Table 3-5 Stakeholder Management Strategy

## Slide 15: Initiating (4 of 5)
Drafting the project charter
  See Table 3-6 for an example
Holding a project kick-off meeting
  It’s good practice to hold a kick-off meeting at the beginning of a project so that stakeholders can meet each other, review the goals of the project, and discuss future plans

## Slide 16: Initiating (5 of 5)

## Slide 17: Project Planning (1 of 3)
The main purpose of project planning is to guide execution
  Every knowledge area includes planning information (see Table 3-7)
Key outputs included in the JWD project
  Team contract
  Project scope statement
  Work breakdown structure (WBS)
  Project schedule, in the form of a Gantt chart with all dependencies and resources entered
  List of prioritized risks (part of a risk register)
See sample documents

## Slide 18: Project Planning (2 of 3)

## Slide 19: Project Planning (3 of 3)
Ranking | Potential Risk
1 | Lack of inputs from internal consultants
2 | Lack of inputs from client representatives
3 | Security of new system
4 | Outsourcing/purchasing for the article retrieval and Ask the Expert features
5 | Outsourcing/purchasing for processing online payment transactions
6 | Organizing the templates and examples in a useful fashion
7 | Providing an efficient search feature
8 | Getting good feedback from Michael Chen and other senior consultants
9 | Effectively promoting the new system
10 | Realizing the benefits of the new system within one year
Table 3-10 List of Prioritized Risks

## Slide 20: Project Execution
Usually takes the most resources to perform
  Project managers must use their leadership skills to handle the many challenges that occur during project execution
Table 3-11 lists the knowledge areas, executing processes, and outputs of project execution
  Many project sponsors and customers focus on deliverables related to providing the products, services, or results desired from the project
  It is equally important to document change requests and update planning documents
A milestone report can help focus on completing major milestones

## Slide 21: Best Practice
One way to learn about best practices in project management is by studying recipients of PMI’s Project of the Year award
  The Quartier international de Montreal (QIM), Montreal’s international district, was a 66-acre urban revitalization project in the heart of downtown Montreal
  This $90 million, five-year project turned a once unpopular area into a thriving section of the city with a booming real estate market and has generated $770 million in related construction

## Slide 22: Project Monitoring and Controlling
Involves measuring progress toward project objectives, monitoring deviation from the plan, and taking correction actions
  Affects all other process groups and occurs during all phases of the project life cycle
Outputs include performance reports, change requests, and updates to various plans
  See Table 3-13

## Slide 23: Project Closing
Involves gaining stakeholder and customer acceptance of the final products and services
  Even if projects are not completed, they should be closed out to learn from the past
Outputs may include project files and lessons-learned reports
  Also may include a final report and presentation

## Slide 24: Scrum Roles, Artifacts, and Ceremonies (1 of 5)
Product owner: person responsible for the business value of the project and for deciding what work to do and in what order, as documented in the product backlog
ScrumMaster: person who ensures that the team is productive, facilitates the daily Scrum, enables close cooperation across all roles and functions, and removes barriers that prevent the team from being effective
Scrum team or development team: cross-functional team of five to nine people who organize themselves and the work to produce the desired results for each sprint, which normally lasts two to four weeks

## Slide 25: Scrum Roles, Artifacts, and Ceremonies (2 of 5)
An artifact is a useful object created by people
Scrum artifacts
  Product backlog: list of features prioritized by business value
  Sprint backlog: highest-priority items from the product backlog to be completed within a sprint
  Burndown chart: shows the cumulative work remaining in a sprint on a day-by-day basis

## Slide 26: Scrum Roles, Artifacts, and Ceremonies (3 of 5)
Scrum ceremonies
  Sprint planning session: meeting with the team to select a set of work from the product backlog to deliver during a sprint
  Daily Scrum: short meeting for the development team to share progress and challenges and plan work for the day
  Sprint reviews: meeting in which the team demonstrates to the product owner what it has completed during the sprint
  Sprint retrospectives: meeting in which the team looks for ways to improve the product and the process based on a review of the actual performance of the development team

## Slide 27: Scrum Roles, Artifacts, and Ceremonies (4 of 5)

## Slide 28: Scrum Roles, Artifacts, and Ceremonies (5 of 5)
Process Group | Scrum Activity
Initiating | 
 | Determine roles
 | Decide how many sprints will compose each release and the scope of software to deliver
Planning | 
 | Create product backlog
 | Create sprint backlog
 | Create release backlog
 | Plan work each day in the daily Scrum
 | Document stumbling blocks in a list
Executing | 
 | Complete tasks each day during sprints
 | Produce a shippable product at the end of each sprint
Table 3-18 Unique Scrum activities by process group

## Slide 29: Project Pre-Initiation and Initiation
Main differences between pre-initiation in this case and the first case
  Determining roles and deciding what functionality would be delivered as part of each release
  How many sprints will be required to complete a release
  How many releases of software to deliver

## Slide 30: Planning (1 of 3)
Because Scrum implies that team members work as a self-directed group, coached by the ScrumMaster, a team charter should not be necessary
Descriptions of work are identified in the product and sprint backlogs
More detailed work is documented in technical stories
Team must estimate a velocity or capacity for each sprint

## Slide 31: Planning (2 of 3)

## Slide 32: Planning (3 of 3)
Product Backlog | Sprint Backlog
1. User story templates, samples, and point person | 1. User story templates, samples, and point person
2. WBS templates, samples, and point person | 2. WBS templates, samples, and point person
3. Project schedule templates, samples, and point person | 3. Project schedule templates, samples, and point person
4. Ability to charge customers for some intranet products and services | 4. Ability to charge customers for some intranet products and services
5. Ability to collect user suggestions | 5. Ability to collect user suggestions
6. Business case templates, samples, and point person | 
7. Ask the Expert feature | 
8. Stakeholder management strategy templates, samples, and point person | 
9. Risk register templates, samples, and point person | 
10. Etc. | 
Table 3-19 Product and Sprint Backlogs

## Slide 33: Executing
The most time and money should be spent on executing
  Plans are implemented to create the desired product
Agile approach: team produces several iterations of a potentially shippable product
  Users can access and make suggestions
Communications are different
  Project team meets every morning, physically or virtually

## Slide 34: Monitoring and Controlling (1 of 2)
The two main tools for monitoring and controlling in the Scrum framework
  Daily Scrum: held each morning to plan and communicate work for the day and discuss any risks, issues, or blockers
  Sprint review: work progress within a sprint can be represented on a sprint board maintained by the ScrumMaster
    Burndown chart: an important artifact used to graphically display progress on each sprint

## Slide 35: Monitoring and Controlling (2 of 2)

## Slide 36: Closing
After the sprint review, the ScrumMaster leads a sprint retrospective
  Team reflects on what happened during the sprint
Sprint retrospective is intended to answer two fundamental questions
  What went well during the last sprint that we should continue doing?
  What could we do differently to improve the product or process?

## Slide 37: Chapter Summary
The five project management process groups are initiating, planning, executing, monitoring and controlling, and closing
You can map the main activities of each process group to the ten knowledge areas
Some organizations develop their own information technology project management methodologies
The JWD Consulting case study provides an example of using the process groups and shows several important project documents
The second version of the same case study illustrates how to use Scrum, the leading agile method, to manage the project