## Slide 1: Chapter 5: Project Scope Management
Information Technology Project Management, Ninth Edition
Note: See the text itself for full citations

## Slide 2: Learning Objectives (1 of 2)
List key reasons why good project scope management is important
Describe the process of planning scope management
Discuss methods for collecting and documenting requirements to meet stakeholder needs and expectations
Explain the scope definition process and describe the contents of a project scope statement
Discuss the process for creating a work breakdown structure using the analogy, top-down, bottom-up, and mind-mapping approaches
Explain the importance of validating scope and how it relates to defining and controlling scope

## Slide 3: Learning Objectives (2 of 2)
Given an information technology (IT) project situation, show how recommended approaches for controlling scope can improve the potential for project success
Describe how software can assist in project scope management
Discuss considerations for agile/adaptive environments

## Slide 4: What is Project Scope Management?
Scope refers to all the work involved in creating the products of the project and the processes used to create them
  A deliverable is a product produced as part of a project, such as hardware or software, planning documents, or meeting minutes
Project scope management includes the processes involved in defining and controlling what is or is not included In a project
  Ensures that the project team and stakeholders have the same understanding of what products the project will produce and what processes the project team will use to produce them

## Slide 5: Project Scope Management Processes (1 of 2)
Main processes
  Planning scope management: determining how the project’s scope and requirements will be managed
  Collecting requirements: defining and documenting the features and functions of the products produced during the project as well as the processes used for creating them
  Defining scope: reviewing the project charter, requirements documents, and organizational process assets to create a scope statement
  Creating the WBS: subdividing the major project deliverables into smaller, more manageable components
  Validating scope: formalizing acceptance of the project deliverables
  Controlling scope: controlling changes to project scope throughout the life of the project

## Slide 6: Project Scope Management Processes (2 of 2)

## Slide 7: Planning Scope Management (1 of 2)
The project team uses expert judgment, data analysis, and meetings to develop two important outputs
  Scope management plan (subsidiary part of the project management plan)
  Requirements management plan
Scope management plan contents
  Prepare a detailed project scope statement
  Create a WBS
  Maintain and approve the WBS
  Obtain formal acceptance of the completed project deliverables
  Control requests for changes to the project scope

## Slide 8: Planning Scope Management (2 of 2)
Requirements Management Plan
  The PMBOK® Guide, Sixth Edition, describes a requirement as ““a condition or capability that is necessary to be present in a product, service, or result to satisfy a business need”
The requirements management plan documents how project requirements will be analyzed, documented, and managed
  How to plan, track, and report requirements activities
  How to perform configuration management activities
  How to prioritize requirements
  How to use product metrics
  How to trace and capture attributes of requirements

## Slide 9: Collecting Requirements (1 of 3)
Several ways to collect requirements
  Interviewing stakeholders
  Holding focus groups and facilitated workshops
  Using group creativity and decision-making techniques
  Utilizing questionnaires and surveys
  Conducting observation studies
  Generating ideas by comparing specific project practices or product characteristics (i.e., benchmarking)

## Slide 10: Collecting Requirements (2 of 3)

## Slide 11: Collecting Requirements (3 of 3)
Requirements traceability matrix (RTM): a table that lists requirements, various attributes of each requirement, and the status of the requirements to ensure that all requirements are addressed
Requirement No. | Name | Category | Source | Status
R32 | Laptop memory | Hardware | Project charter and corporate laptop specifications | Complete. Laptops ordered meet memory requirement.
Table 5-1 Sample entry in a requirements traceability matrix

## Slide 12: Defining Scope (1 of 2)
Important elements of a project scope statement
  Product scope description
  Product user acceptance criteria
  Detailed information on all project deliverables
It is also helpful to document other scope-related information
  Project boundaries, constraints, and assumptions
  Supporting document references (e.g., product specifications)
As time progresses, the scope of a project should become more clear and specific

## Slide 13: Sample Project Charter (partial)

## Slide 14: Defining Scope (2 of 2)
Project Charter: Upgrades may affect servers . . . (listed under Project Objectives)
Project Scope Statement, Version 1: Servers: If additional servers are required to support this project, they must be compatible with existing servers. If it is more economical to enhance existing servers, a detailed description of enhancements must be submitted to the CIO for approval. See current server specifications provided in Attachment 6. The CEO must approve a detailed plan describing the servers and their location at least two weeks before installation.
Project Scope Statement, Version 2: Servers: This project will require purchasing 10 new servers to support Web, network, database, application, and printing functions. Virtualization will be used to maximize efficiency. Detailed descriptions of the servers are provided in a product brochure in Attachment 8, along with a plan describing where they will be located.
Table 5-3 Further defining project scope

## Slide 15: Creating the Work Breakdown Structure (1 of 9)
Work Breakdown Structure (WBS) is a deliverable-oriented grouping of the work involved in a project that defines the total scope of the project
  Foundation document that provides the basis for planning and managing project schedules, costs, resources, and changes
Decomposition is the main tool or technique for creating a WBS
  Subdividing project deliverables into smaller pieces
  A work package is a task at the lowest level of the WBS
Outputs of creating the WBS are the scope baseline and project documents updates
  Scope baseline includes the approved project scope statement and its associated WBS and WBS dictionary

## Slide 16: Creating the Work Breakdown Structure (2 of 9)

## Slide 17: Creating the Work Breakdown Structure (3 of 9)

## Slide 18: Creating the Work Breakdown Structure (4 of 9)

## Slide 19: Creating the Work Breakdown Structure (5 of 9)

## Slide 20: Creating the Work Breakdown Structure (6 of 9)
1.0 Software Product Release 5.0 |  | 
 | 1.1 Project Management | 
 |  | 1.1.1 Planning
 |  | 1.1.2 Meetings
 |  | 1.1.3 Administration
 | 1.2 Product Requirements | 
 |  | 1.2.1 Software
 |  | 1.2.2 User Documentation
 |  | 1.2.3 Training Program Materials
 | 1.3 Detail Design | 
 |  | 1.3.1 Software
 |  | 1.3.2 User Documentation
 |  | 1.3.2 User Documentation
 | 1.4 Construct | 
 |  | 1.4.1 Software
 |  | 1.4.2 User Documentation
 |  | 1.4.3 Training Program Materials
 | 1.5 Integration and Test | 
 |  | 1.5.1 Software
 |  | 1.5.2 User Documentation
 |  | 1.5.3 Training Program Materials
Table 5-4 Tabular form of WBS

## Slide 21: Creating the Work Breakdown Structure (7 of 9)
Approaches to developing work breakdown structures
  Using guidelines: some organizations, like the U.S. Department of Defense (DOD), provide guidelines for preparing WBSs
  Analogy approach: review WBSs of similar projects and tailor to your project
  Top-down approach: start with the largest items of the project and break them down
  Bottom-up approach: start with the specific tasks
  Mind mapping: uses branches radiating out from a core idea to structure thoughts and ideas

## Slide 22: Creating the Work Breakdown Structure (8 of 9)

## Slide 23: Creating the Work Breakdown Structure (9 of 9)

## Slide 24: The WBS Dictionary (1 of 3)
Many WBS tasks are vague
  WBS dictionary is a document that describes detailed information about each WBS item
    Format of the WBS dictionary can vary based on project needs

## Slide 25: The WBS Dictionary (2 of 3)
WBS Dictionary Entry March 20
Project Title: Information Technology (IT) Upgrade Project
WBS Item Number: 2.2
WBS Item Name: Database Update
Description: The IT department maintains an online database of hardware and software on the corporate intranet. We need to make sure that we know exactly what hardware and software employees are currently using and if they have any unique needs before we decide what to order for the upgrade. This task will involve reviewing information from the current database, producing reports that list each department’s employees and location, and updating the data after performing the physical inventory and receiving inputs from department managers. Our project sponsor will send a notice to all department managers to communicate the importance of this project and this particular task. In addition to general hardware and software upgrades, the project sponsors will ask the department managers to provide information for any unique requirements they might have that could affect the upgrades. This task also includes updating the inventory data for network hardware and software. After updating the inventory database, we will send an e-mail to each department manager to verify the information and make changes online as needed. Department managers will be responsible for ensuring that their people are available and cooperative during the physical inventory. Completing this task is dependent on WBS Item Number 2.1, Physical Inventory, and must precede WBS Item Number 3.0, Hardware and Software Acquisition.
Table 5-5 Sample WBS dictionary entry

## Slide 26: The WBS Dictionary (3 of 3)
Advice for creating a WBS and WBS dictionary
  Unit of work should appear at only one place in the WBS
  Work content of a WBS item is the sum of the WBS items below it
  WBS item is the responsibility of only one individual, even though many people may be working on it
  WBS must be consistent with the way in which work is actually going to be performed; it should serve the project team first, and other purposes only if practical
  Project team members should be involved in developing the WBS to ensure consistency and buy-in
  Each WBS item must be documented in a WBS dictionary to ensure accurate understanding of the scope of work included and not included
  WBS must be a flexible tool to accommodate inevitable changes while properly maintaining control of the work content in the project according to the scope statement

## Slide 27: Validating Scope
It is difficult to create a good project scope statement and WBS for a project
  Even more difficult, especially on IT projects, to verify the project scope and minimize scope changes
Even when the project scope is fairly well defined, many IT projects suffer from scope creep
  Tendency for project scope to keep getting bigger and bigger
Scope validation involves formal acceptance of the completed project deliverables
  Acceptance is often achieved by a customer inspection and then sign-off on key deliverables

## Slide 28: Global Issues
Many countries have had difficulties controlling the scope of large projects
  Especially those that involve advanced technologies and many different users
    For example, the state government of Victoria, Australia, has a website for its public transportation smart card; there were many problems in developing and implementing the smart card

## Slide 29: Controlling Scope (1 of 3)
Scope control involves controlling changes to the project scope
  Keeping project goals and business strategy in mind
Goals of scope control
  Influence the factors that cause scope changes
  Ensure changes are processed according to procedures developed as part of integrated change control
  Manage changes when they occur
Variance is the difference between planned and actual performance

## Slide 30: Controlling Scope (2 of 3)
Suggestions for improving user input
  Develop a good project selection process and insist that sponsors are from the user organization
  Place users on the project team
  Conduct regular meetings with defined agendas
  Deliver something to users and sponsors on a regular basis
  Do not promise to deliver what the team cannot deliver in a particular time frame
  Locate users with the developers

## Slide 31: Controlling Scope (3 of 3)
Suggestions for reducing incomplete and changing requirements
  Develop and follow a requirements management process
  Employ techniques such as prototyping, use case modeling, and JAD to get more user involvement
  Put requirements in writing and keep them current
  Create a requirements management database for documenting and controlling requirements
  Provide adequate testing and conduct it throughout the project life cycle
  Review changes from a systems perspective
  Emphasize completion dates to help focus on what’s most important
  Allocate resources specifically for handling change requests

## Slide 32: Using Software to Assist in Project Scope Management
Word-processing software helps create several scope-related documents
Spreadsheets or presentation software to develop various charts, graphs, and matrixes related to scope management
Mind-mapping software can be useful in developing a WBS
Communication software like e-mail and web-based applications can transmit project scope management information
Project management software helps in creating a WBS; basis for creating a Gantt chart
Specialized software is available to assist in project scope management

## Slide 33: Considerations for Agile/Adaptive Environments
Stakeholders define and approve the detailed scope before the start of an iteration with an adaptive or agile product life cycle, producing a usable product at the end of each iteration
  Detailed scope develops over time
Agile approach provides several usable products during the project

## Slide 34: Chapter Summary
Project scope management includes the processes required to ensure that the project addresses all the work required, and only the work required, to complete the project successfully
  Main processes
    Define scope management
    Collect requirements
    Define scope
    Create WBS
    Validate scope
    Control scope