## Slide 1: Chapter 9: Project Resource Management
Information Technology Project Management, Ninth Edition
Note: See the text itself for full citations

## Slide 2: Learning Objectives (1 of 2)
Explain the importance of good resource management on projects, including the current state of the global IT workforce and future implications for IT
Define project resource management and understand its processes
Summarize key concepts for managing people by understanding theories of motivation, influence, and power; how people and teams can become more effective; emotional intelligence; and leadership
Discuss resource management planning and be able to create a human resource plan, project organizational chart, responsibility assignment matrix, and resource histogram
Describe the process of estimating activity resources

## Slide 3: Learning Objectives (2 of 2)
Discuss issues that are typically involved in resource acquisition, particularly as they involve resource assignments, resource loading, and resource leveling
Assist in team development with training, team-building activities, and reward systems
Explain and apply several tools and techniques to help manage a project team and summarize general advice on managing teams
Summarize the process of controlling resources
Describe how project management software can assist in project resource management
Discuss considerations for agile/adaptive environments

## Slide 4: The Importance of Resource Management
People determine the success and failure of organizations and projects
  Most project managers agree that managing human resources effectively is one of the toughest challenges they face
  Managing people is a vital component of project resource management

## Slide 5: Implications for the Future of IT Human Resource Management
Proactive organizations are addressing human resource needs
  Improving benefits
  Redefining work hours and incentives
  Finding future workers

## Slide 6: What is Project Resource Management? (1 of 2)
Making the most effective use of the human and physical resources involved with a project
  Planning resource management
  Estimating activity resources
  Acquiring resources
  Developing the project team
  Managing the project team
  Controlling resources

## Slide 7: What is Project Resource Management? (2 of 2)

## Slide 8: Keys to Managing and Leading People
Psychologists and management theorists have devoted much research and thought to the field leading people at work
  Motivation theories
  Influence and power
  Effectiveness
  Emotional intelligence
  Leadership

## Slide 9: Motivation Theories
Intrinsic motivation causes people to participate in an activity for their own enjoyment
  Example: some people love to read, write, or play an instrument because it makes them feel good
Extrinsic motivation causes people to do something for a reward or to avoid a penalty
  Example: some young children would prefer not to play an instrument, but they do because they receive a reward or avoid a punishment for doing so

## Slide 10: Maslow’s Hierarchy of Needs (1 of 2)
Abraham Maslow argued that humans possess unique qualities that enable them to make independent choices, thus giving them control of their destiny
  Developed a hierarchy of needs; states that people’s behaviors are guided or motivated by a sequence of needs

## Slide 11: Maslow’s Hierarchy of Needs (2 of 2)

## Slide 12: Herzberg’s Motivational-Hygiene Theory (1 of 2)
Frederick Herzberg distinguished between motivational factors and hygiene factors
  Motivational factors: factors that cause job satisfaction
  Hygiene factors: could cause job dissatisfaction

## Slide 13: Herzberg’s Motivational-Hygiene Theory (2 of 2)
Hygiene Factors | Motivators
Larger salaries | Achievement
More supervision | Recognition
More attractive work environment | Work itself
Computer or other required equipment | Responsibility
Health benefits | Advancement
Training | Growth
Table 9-1 Examples of Herzberg’s hygiene factors and
motivators

## Slide 14: Influence and Power (1 of 3)
Thamhain and Wilemon: ways to have influence on projects
  Authority: legitimate hierarchical right to issue orders
  Assignment: ability to influence a worker's later work assignments
  Budget: ability to authorize others' use of discretionary funds
  Promotion: ability to improve a worker's position
  Money: ability to increase a worker's pay and benefits
  Penalty: ability to cause punishment
  Work challenge: ability to assign work that capitalizes on a worker's enjoyment of doing a particular task
  Expertise: perceived special knowledge that others deem important
  Friendship: ability to establish friendly personal relationships between the project manager and others

## Slide 15: Influence and Power (2 of 3)
Ways to influence
  Project managers who use work challenges and expertise to influence people projects are more likely to succeed
  Projects are more likely to fail when project managers rely too heavily on authority, money, or penalty

## Slide 16: Influence and Power (3 of 3)
Power is the potential ability to influence behavior to get people to do things they would not otherwise do
  Power is much stronger than influence, because it is often used to force people to change their behavior
Types of power
  Coercive
  Legitimate
  Expert
  Reward
  Referent

## Slide 17: Emotional Intelligence
Howard Gardner’s book Frames of Mind: The Theory of Multiple Intelligences introduced the concept of using more than one way to think of and measure human intelligence
  Gardner suggested the need to develop both interpersonal intelligence (capacity to understand the motivations, intentions, and desires of others) and intrapersonal intelligence (capacity to understand oneself, one’s feelings, and motivations)
  Emotional intelligence (EI) is knowing and managing one’s own emotions and understanding the emotions of others for improved performance

## Slide 18: Leadership
There is no one best way to be a leader
  Most experts agree that the best leaders are able to adapt their style to needs of the situation
  It is important to understand and pay attention to concepts of motivation, influence, power, effectiveness, emotional intelligence, and leadership in all project processes

## Slide 19: Developing the Resource Management Plan and Team Charter (1 of 6)
Involves identifying and documenting project resources, roles, responsibilities, skills, and reporting relationships
  Can be separated into a human resource management plan and a physical resource management plan
Contents include:
  Project organizational charts
  Responsibility assignment matrixes
  Staffing management plan and resource histograms
  Team charters

## Slide 20: Developing the Resource Management Plan and Team Charter (2 of 6)

## Slide 21: Developing the Resource Management Plan and Team Charter (3 of 6)

## Slide 22: Developing the Resource Management Plan and Team Charter (4 of 6)

## Slide 23: Developing the Resource Management Plan and Team Charter (5 of 6)
 | Car Owner | Shop Owner | Mechanic | Parts Supplier
Pay for parts and services | A, R | C |  | 
Determine parts and services needed | C |  | A, R | C
Supply parts |  | C | C | A, R
Install parts | I | A | R | 
Table 9-2 Sample RACI chart

## Slide 24: Developing the Resource Management Plan and Team Charter (6 of 6)

## Slide 25: Estimating Activity Resources
Tools that can assist in resource estimating
  Expert judgment
  Various estimating approaches
  Data analysis
  Project management software
  Meetings

## Slide 26: Acquiring Resources
During the late 1990s, the IT job market became extremely competitive
  Today, many organizations again face a shortage of IT staff
Regardless of the current job market, acquiring qualified IT professionals is critical

## Slide 27: Resource Assignment
After developing resource requirements, project managers must work with other people in their organizations to assign them to their projects or to acquire additional human or physical resources needed for the project
  Organizations that do a good job of staff acquisition have good staffing plans
  It is very important to consider the needs of individuals and the organization when making recruiting and retention decisions

## Slide 28: Resource Loading (1 of 2)
Resource loading refers to the amount of individual resources an existing schedule requires during specific time periods
  Helps project managers develop a general understanding of the demands a project will make on the organization’s resources and individual people’s schedules
Overallocation means more resources than available are assigned to perform work at a given time

## Slide 29: Resource Loading (2 of 2)

## Slide 30: Resource Leveling (1 of 2)
Resource leveling is a technique for resolving resource conflicts by delaying tasks
  Main purpose is to create a smoother distribution of resource usage
Benefits of resource leveling
  When resources are used on a more constant basis, they require less management
  May enable project managers to use a just-in-time inventory type of policy for using subcontractors or other expensive resources
  Results in fewer problems for project personnel and accounting department
  Often improves morale

## Slide 31: Resource Leveling (2 of 2)

## Slide 32: Developing the Project Team (1 of 2)
The main goal of team development is to help people work together more effectively to improve project performance
  It takes teamwork to successfully complete most projects
Tuckman model describes five stages of team development
  Forming
  Storming
  Norming
  Performing
  Adjourning

## Slide 33: Developing the Project Team (2 of 2)
Training
  Project managers often recommend that people take specific training courses to improve individual and team development
Team-building activities
  Physical challenges
  Psychological preference indicator tools

## Slide 34: The Social Styles Profile
People are perceived as behaving primarily in one of four zones, based on their assertiveness and responsiveness
  Drivers
  Expressives
  Analyticals
  Amiables

## Slide 35: DISC Profile
Four-dimensional model of normal behavior
  Dominance
  Influence
  Steadiness
  Compliance

## Slide 36: Reward and Recognition Systems
Team-based reward and recognition systems can promote teamwork
  Focus on rewarding teams for achieving specific goals
    If management rewards teamwork, they will promote or reinforce the philosophy that people work more effectively in teams
Project managers must continually assess their team’s performance
  When they find areas in which individuals or the entire team can improve, it’s their job to find the best way to develop their people and improve performance

## Slide 37: Managing the Project Team
Project managers must lead their teams in performing various project activities
After assessing team performance and related information, the project manager must make several decisions
  Changes to be requested
  Corrective or preventive actions
  Updates needed

## Slide 38: Tools and Techniques for Managing Project Teams (1 of 4)
Several tools and techniques are available to assist in managing project teams
  Interpersonal and team skills
  Project management information systems
  Conflict management

## Slide 39: Tools and Techniques for Managing Project Teams (2 of 4)
Conflict handling modes
  Confrontation: directly face a conflict using a problem-solving approach
  Compromise: use a give-and-take approach
  Smoothing: de-emphasize areas of difference and emphasize areas of agreement
  Forcing: win-lose approach
  Withdrawal: retreat or withdraw from an actual or potential disagreement
  Collaborating: decision makers incorporate different viewpoints and insights to develop consensus and commitment

## Slide 40: Tools and Techniques for Managing Project Teams (3 of 4)

## Slide 41: Tools and Techniques for Managing Project Teams (4 of 4)
Conflict can be good
  Conflict often produces important results, such as new ideas, better alternatives, and motivation to work harder and more collaboratively
  Groupthink: conformance to the values or ethical standards of a group; can develop if there are no conflicting viewpoints
  Research suggests that task-related conflict often improves team performance, but emotional conflict often depresses team performance

## Slide 42: General Advice on Managing Teams (1 of 2)
Five dysfunctions of teams
  Absence of trust
  Fear of conflict
  Lack of commitment
  Avoidance of accountability
  Inattention to results
General advice
  Be patient and kind with your team
  Fix the problem instead of blaming people
  Establish regular, effective meetings
  Allow time for teams to go through the basic team-building stages
  Limit the size of work teams to three to seven members
  Plan some social activities to help project team members and other stakeholders get to know each other better
  Stress team identity
  Nurture team members and encourage them to help each other
  Acknowledge individual and group accomplishments
  Take additional actions to work with virtual team members

## Slide 43: Controlling Resources
Ensuring physical resources assigned to the project are available as planned
  Also involves monitoring the planned versus actual resources utilization and taking corrective actions as needed

## Slide 44: Using Software to Assist in Resource Management
Software can help in producing a simple responsibility assignment matrix or resource histograms
Software includes several features related to human resource management
  Assigning and tracking resources
  Leveling resources
  Resource usage reports
  Overallocated resource reports
  To-do lists

## Slide 45: Considerations for Agile/Adaptive Environments
Teams are important on all types of projects, as is collaboration, problem solving, and knowledge sharing
  On agile projects, team members are usually fully dedicated to a single team
    Relationships are based on trust, and collaboration is continuously improved using regular feedback

## Slide 46: Chapter Summary
Project resource management includes the processes required to make the most effective use of the people involved with a project
  Planning resources
  Estimating activity resources
  Acquiring resources
  Developing the team
  Managing the team
  Controlling resources