## Slide 1: Chapter 10: Project Communications Management
Information Technology Project Management, Ninth Edition
Note: See the text itself for full citations

## Slide 2: Learning Objectives (1 of 2)
Discuss the role of soft skills in IT project management, and highlight the importance of good communications as one means of achieving project success
Review key concepts related to communications
Explain the elements of planning project communications and how to create a communications management plan
Describe how to manage communications, including communication technologies, media, and performance reporting
Discuss methods for controlling communications to ensure that information needs are met throughout the life of the project
List various methods for improving project communications, such as running effective meetings, using various technologies effectively, and using templates

## Slide 3: Learning Objectives (2 of 2)
Describe how software can enhance project communications management
Discuss considerations for agile/adaptive environments

## Slide 4: The Importance of Project Communications Management (1 of 2)
Greatest threat to many projects is a failure to communicate
  You cannot totally separate technical skills and soft skills when working on IT projects
  For projects to succeed, every project team member needs both types of skills
Main processes in project communications management
  Planning communications management
  Managing communications
  Monitoring communications

## Slide 5: The Importance of Project Communications Management (2 of 2)
Notes: .

## Slide 6: Keys to Good Communications
Project managers say they spend as much as 90 percent of their time communicating
  Several important concepts can help
    Focus on group and individual communication needs
    Use formal and informal methods for communicating
    Distribute important information in an effective and timely manner
    Set the stage for communicating bad news
    Determine the number of communication channels

## Slide 7: Focusing on Group and Individual Communication Needs
People are not interchangeable parts
  As illustrated in Brooks’ book The Mythical Man-Month, you cannot assume that a task originally scheduled to take two months of one person’s time can be done in one month by two people
    Nine women cannot produce a baby in one month
Every person is unique, so you cannot simply generalize based on a personality profile or other traits
  Seek first to understand, as author Stephen Covey suggests in The 7 Habits of Highly Effective People
    Put yourself in someone else’s shoes before you can truly communicate

## Slide 8: Formal and Informal Methods for Communicating
Many people prefer informal communications
  Several colleagues and managers want to know the people working on their projects and develop a trusting relationship with them
  Oral communication also helps build stronger relationships among project personnel and project stakeholders
  Effective creation and distribution of information depends on project managers and project team members having good communication skills

## Slide 9: Distributing Information in an Effective and Timely Manner
Important considerations
  Include detailed technical information that affects critical performance features of products or services
  Document any changes in technical specifications that might affect product performance
  Report bad news
  Have short, frequent meetings

## Slide 10: Setting the Stage for Communicating Bad News
It is important to put information in context, especially if it’s bad news
  If there is a problem, know how it will affect the whole project and the organization
    Recommend steps to take to mitigate a problem
Project managers should know how a major problem might affect the bottom line of the organization
  Use leadership skills to handle the challenge

## Slide 11: Determining the Number of Communications Channels (1 of 2)
As the number of people involved increases, the complexity of communications increases
  More communications channels or pathways through which people can communicate
  Number of communications channels = n(n-1)/2
  (where n is the number of people involved)

## Slide 12: Determining the Number of Communications Channels (2 of 2)

## Slide 13: Planning Communications Management (1 of 3)
Every project should include some type of communications management plan
  Guides project communications
  Varies with the needs of the project, but some type of written plan should always be prepared
    For small projects, the communications management plan can be part of the team contract
    For large projects, it should be a separate document

## Slide 14: Planning Communications Management (2 of 3)
Communications management plan contents
  Stakeholder communications requirements
  Information to be communicated, including format, content, and level of detail
  Who will receive the information and who will produce it
  Suggested methods or technologies for conveying the information
  Frequency of communication
  Escalation procedures for resolving issues
  Revision procedures for updating the communications management plan
  A glossary of common terminology

## Slide 15: Planning Communications Management (3 of 3)
Stakeholders | Document Name | Document Format | Contact Person | Due
Customer management | Monthly status report | Hard copy and meeting | Tina Erndt, Tom Silva | First of month
Customer business staff | Monthly status report | Hard copy | Julie Grant, Sergey Cristobal | First of month
Customer technical staff | Monthly status report | E-mail | Li Chau, Nancy Michaels | First of month
Internal management | Monthly status report | Hard copy and meeting | Bob Thomson | First of month
Internal business and technical staff | Monthly status report | Intranet | Angie Liu | First of month
Training subcontractor | Training plan | Hard copy | Jonathan Kraus | November 1
Software subcontractor | Software implementation plan | E-mail | Najwa Gates | June 1
Comments: Put the titles and dates of documents in e-mail headings and have recipients acknowledge receipt.
Table 10-1 Sample stakeholder communications analysis

## Slide 16: Managing Communications
Managing communications is a large part of a project manager’s job
  Getting project information to the right people at the right time and in a useful format is just as important as developing the information in the first place
Important considerations
  Use of technology
  Appropriate methods and media to use
  Performance reporting

## Slide 17: Using Technology to Enhance Creation and Distribution
Technology can facilitate the process of creating and distributing information, when used effectively
  It is important to select the appropriate communication method and media

## Slide 18: Selecting the Appropriate Communication Methods and Media
Classifications for communication methods
  Interactive communication: two or more people interact to exchange information via meetings, phone calls, or video conferencing
    Most effective way to ensure common understanding
  Push communication: information is sent or pushed to recipients without their request via reports, e-mails, faxes, voice mails, and other means
    Ensures that the information is distributed, but does not ensure that it was received or understood
  Pull communication: information is sent to recipients at their request via websites, bulletin boards, e-learning, knowledge repositories like blogs, and other means

## Slide 19: Reporting Performance
Performance reporting keeps stakeholders informed about how resources are being used to achieve project objectives
  Progress reports describe what the project team has accomplished during a certain period of time
  Status reports describe where the project stands at a specific point in time
  Forecasts predict future project status and progress based on past information and trends

## Slide 20: Monitoring Communications
Main goal of monitoring communications is to ensure the optimal flow of information throughout the entire project life cycle
  The project manager and project team should use expert judgment, project management information systems, data representation, interpersonal and team skills, and meetings to assess how well communications are working
    If problems exist, the project manager and team need to take action, which often requires changes to the earlier processes of planning and managing project communications
  It is often beneficial to have a facilitator from outside the project team assess how well communications are working

## Slide 21: Suggestions for Improving Project Communications
Good communication is vital to the management and success of IT projects
  Develop better communication skills
  Run effective meetings
  Use e-mail and other technologies effectively
  Employ templates for project communications

## Slide 22: Developing Better Communication Skills
Most companies spend a lot of money on technical training for employees, even when employees might benefit more from communications training
  Individual employees are more likely to enroll voluntarily in classes to learn the latest technology than in classes that develop soft skills
  As organizations become more global, they realize they must invest in ways to improve communication with people from different countries and cultures
  It takes leadership to improve communication

## Slide 23: Running Effective Meetings
Guidelines to help improve time spent at meetings
  Determine if a meeting can be avoided
  Define the purpose and intended outcome of the meeting
  Determine who should attend the meeting
  Provide an agenda to participants before the meeting
  Prepare handouts and visual aids, and make logistical arrangements ahead of time
  Run the meeting professionally
  Set the ground rules for the meeting
  Build relationships

## Slide 24: Using E-Mail, Instant Messaging, Texting, Kanban Boards, and Collaborative Tools Effectively (1 of 2)
Guidelines to use e-mail as a more effective communication tool
  Be sure to send information to the right people
  Use meaningful subject lines and limit the content of emails to one main subject
  Be as clear and concise as possible
  Reread your e-mail before you send it
  Limit the number and size of e-mail attachments
  Delete e-mail that you do not need to save or that does not require a response
  Make sure the virus protection software is up to date
  Respond to e-mail quickly
  If you need to keep e-mail, file each message appropriately

## Slide 25: Using E-Mail, Instant Messaging, Texting, Kanban Boards, and Collaborative Tools Effectively (2 of 2)
Guidelines to help use other communication tools more effectively
  Make sure that your team is using a good tool
  Be sure to authorize the right people to share your collaborative documents
  Make sure that the right person can authorize changes to shared documents and that you back up files
  Develop a logical structure for organizing and filing shared documents

## Slide 26: Using Templates for Project Communications (1 of 4)
Many people are afraid to ask for help
  Providing examples and templates for project communications saves time and money
  Finding, developing, and sharing relevant templates and sample documents are important tasks for many project managers
The project manager and project team members should prepare a lessons-learned report
  Reflective statement that documents important information they have learned from working on the project
Project teams can use one of the many software products available to assist in project communications through the Web
  Vary considerably in price and functionality

## Slide 27: Using Templates for Project Communications (2 of 4)

## Slide 28: Using Templates for Project Communications (3 of 4)

## Slide 29: Using Templates for Project Communications (4 of 4)

## Slide 30: Using Software to Assist in Project Communications (1 of 2)
Many organizations are discovering how valuable project management software can be in communicating project information across the organization
  Project management software can provide different views of information to help meet various communication needs
  Often, one of the biggest communication problems on projects is providing the most recent project plans, Gantt charts, specifications, meeting information, and change requests to stakeholders in a timely fashion
  Most project management software allows users to insert hyperlinks to other project-related files

## Slide 31: Using Software to Assist in Project Communications (2 of 2)
Many project management software products also provide tools to enhance communications
  Portfolio management
  Resource management
  Project collaboration
Even with all of the technology available, many organizations have problems communicating on global projects
  Issues with timing, audio, and video
  Differences in culture and language

## Slide 32: Considerations For Agile/Adaptive Environments (1 of 2)
Communications should be up to date, easily available, and reviewed regularly with stakeholders
  Many projects involve people who do not work in close proximity to each other
    Effectively planning for good project communications and using appropriate technology become even more important in these situations

## Slide 33: Considerations For Agile/Adaptive Environments (2 of 2)
Communication is among the more important factors for success in project management
  Technology can aid in the communications process and be the easiest aspect of the process to address, it is not the most important
  Improving an organization’s ability to communicate is vital; often requires a cultural change in an organization that takes a lot of time, hard work, and patience

## Slide 34: Chapter Summary (1 of 2)
Failure to communicate is often the greatest threat to the success of any project, especially IT projects
  Communication is the oil that keeps a project running smoothly
  Project communications management involves planning communications management, managing communications, and controlling communications
Project managers can spend as much as 90 percent of their time on communicating
  There are several keys to good communications
A communications management plan of some type should be created for all projects to help ensure good communications
  Contents will vary based on the needs of the project

## Slide 35: Chapter Summary (2 of 2)
Managing communication includes creating and distributing project information
  Various methods for distributing project information include formal, informal, written, and verbal
To improve project communications, project managers and their teams must develop their communication skills
  Suggestions for improving project communications include learning how to run more effective meetings, how to use e-mail, instant messaging, texting, kanban boards, and collaborative software more effectively, and how to use templates for project communications
New hardware and software continue to become available to help improve communications.