## Slide 1: Chapter 12: Project Procurement Management
Information Technology Project Management, Ninth Edition
Note: See the text itself for full citations

## Slide 2: Learning Objectives (1 of 2)
Explain the importance of project procurement management and the increasing use of outsourcing for information technology (IT) projects
Describe the work involved in planning procurements for projects, including determining the proper type of contract to use and preparing a procurement management plan, statement of work, source selection criteria, and make-or-buy analysis
Discuss how to conduct procurements and strategies for obtaining seller responses, selecting sellers, and awarding contracts
Describe the process of controlling procurements by managing procurement relationships and monitoring contract performance

## Slide 3: Learning Objectives (2 of 2)
Discuss types of software that are available to assist in project procurement management
Discuss considerations for agile/adaptive environments

## Slide 4: Importance of Project Procurement Management (1 of 4)
Procurement means acquiring goods and/or services from an outside source
  Other terms include purchasing and outsourcing
Garner estimated the value of the global IT industry in 2017 at $3.7 trillion
  According to a study by Deloitte, the outsourcing market continues to grow
Debates on outsourcing
  Some companies, such as Wal-Mart, prefer to do no outsourcing at all, while others do a lot of outsourcing
  GM recently announced plans to switch from outsourcing 90% of IT service to only 10%

## Slide 5: Importance of Project Procurement Management (2 of 4)
Why outsource?
  Access skills and technologies
  Reduce both fixed and recurrent costs
  Allow the client organization to focus on its core business
  Provide flexibility
  Increase accountability

## Slide 6: Importance of Project Procurement Management (3 of 4)
Project procurement management
  Acquiring goods and services for a project from outside the performing organization
Main processes
  Planning procurement management: determining what to procure and when and how to do it
  Conducting procurements: obtaining seller responses, selecting sellers, and awarding contracts
  Controlling procurements: managing relationships with sellers, monitoring contract performance, making changes as needed, and closing out contracts

## Slide 7: Importance of Project Procurement Management (4 of 4)

## Slide 8: Planning Procurement Management
Identifying which project needs can best be met by using products or services outside the organization
  Involves deciding whether to procure, how to procure, what to procure, how much to procure, and when to procure
  An important output of this process is the make-or-buy decision
  If there is no need to buy any products or services from outside the organization, then there is no need to perform any of the other procurement management processes

## Slide 9: Types of Contracts (1 of 3)
Different types of contracts can be used in different situations
  Fixed price or lump sum contracts: involve a fixed total price for a well-defined product or service
    Point of Total Assumption (PTA): cost at which the contractor assumes total responsibility for each additional dollar of contract cost
  Cost-reimbursable contracts: involve payment to the seller for direct and indirect costs
    Cost plus incentive fee, cost plus fixed fee, and cost plus percentage of costs
  Time and material contracts: hybrid of both fixed price and cost reimbursable contracts
  Unit price contracts: require the buyer to pay the seller a predetermined amount per unit of service

## Slide 10: Types of Contracts (2 of 3)

## Slide 11: Types of Contracts (3 of 3)
Contracts should include specific clauses to take into account issues unique to the project
  Time and material contracts and unit-price contracts can be high or low risk, depending on the nature of the project and other contract clauses
  A termination clause allows the buyer or supplier to end the contract

## Slide 12: Tools and Techniques for Planning Procurement Management
Several tools and techniques are available to help project managers and their teams in planning procurement management
  Make-or-buy analysis
    General management technique used to determine whether an organization should make or perform a particular product or service inside the organization or buy from someone else
  Expert judgment
    Experts both from inside and outside an organization can provide excellent advice in planning purchases and acquisitions
  Market research
    Many potential suppliers are often available for goods and services, so the project team must choose suppliers carefully

## Slide 13: Procurement Management Plan
Describes how the procurement processes will be managed, from developing documentation for making outside purchases or acquisitions to contract closure
  Contents varies based on project needs

## Slide 14: Statement of Work (1 of 2)
A statement of work (SOW) is a description of the work required for the procurement
  If a SOW is used as part of a contract to describe only the work required for that particular contract, it is called a contract statement of work
  A contract SOW is a type of scope statement
  A good SOW gives bidders a better understanding of the buyer’s expectations

## Slide 15: Statement of Work (2 of 2)

## Slide 16: Procurement or Bid Documents
Request for Proposals: used to solicit proposals from prospective sellers
  A proposal is a document prepared by a seller when there are different approaches for meeting buyer needs
Requests for Quotes: used to solicit quotes or bids from prospective suppliers
  A bid, also called a tender or quote (short for quotation), is a document prepared by sellers providing pricing for standard items that have been clearly defined by the buyer

## Slide 17: Source Selection Criteria
It’s important to prepare some form of evaluation criteria, preferably before issuing a formal RFP or RFQ
  Organizations use criteria to rate or score proposals, and they often assign a weight to each criterion to indicate its importance
Beware of proposals that look good on paper
  Be sure to evaluate factors, such as past performance and management approach
Some IT projects also require potential sellers to deliver a technical presentation as part of their proposal
  The proposed project manager should lead the potential seller’s presentation team

## Slide 18: Conducting Procurements (1 of 4)
Steps after planning for procurement management
  Decide whom to ask to do the work
  Send appropriate documentation to potential sellers
  Obtain proposals or bids
  Select a seller
  Award a contract

## Slide 19: Conducting Procurements (2 of 4)
Approaches for procurement
  Organizations can advertise to procure goods and services in several ways
    Approaching the preferred supplier
    Approaching several potential suppliers and taking bids
A bidders’ conference can help clarify expectations
  Meeting with prospective sellers prior to preparation of their proposals or bids

## Slide 20: Conducting Procurements (3 of 4)

## Slide 21: Conducting Procurements (4 of 4)
Seller selection
  After developing a short list of possible sellers, organizations often follow a more detailed proposal evaluation process
  It is customary to have contract negotiations during the source selection process
  Sellers on the short list often prepare a best and final offer (BAFO)
  Final output is a contract signed by the buyer and the selected seller

## Slide 22: Controlling Procurements (1 of 4)
Ensures the seller’s performance meets contractual requirements
  Contracts are legal relationships, so it is important that legal and contracting professionals be involved in writing and administering contracts
    Project team members must be aware of potential legal problems they might cause by not understanding a contract
It is critical that project managers and team members watch for constructive change orders
  Oral or written acts or omissions by someone with actual or apparent authority that can be construed to have the same effect as a written change order

## Slide 23: Controlling Procurements (2 of 4)
Suggestions for change control in contracts
  Changes to any part of the project need to be reviewed, approved, and documented by the same people in the same way that the original part of the plan was approved
  Evaluation of any change should include an impact analysis
  Changes must be documented in writing
  Project managers and teams should stay closely involved to make sure the new system will meet business needs and work in an operational environment
  Have backup plans
  Use tools and techniques, such as a contract change control system, buyer-conducted performance reviews, inspections and audits, etc.

## Slide 24: Controlling Procurements (3 of 4)
Closing procurements
  Involves completing and settling contracts and resolving any open items
  The project team should determine if all work was completed correctly and satisfactorily, update records to reflect final results, and archive information for future use
  The contract itself should include requirements for formal acceptance and closure

## Slide 25: Controlling Procurements (4 of 4)
Tools to assist in contract closure
  Procurement audits identify lessons learned in the procurement process
  A records management system provides the ability to easily organize, find, and archive procurement-related documents
  Ideally, all procurements should end in a negotiated settlement between the buyer and the seller; if negotiation is not possible, then some type of alternate dispute resolution such as mediation or arbitration can be used
  Archiving information for future use is particularly important

## Slide 26: Using Software to Assist in Project Procurement Management (1 of 2)
Word-processing software: write proposals and contracts
Spreadsheet software: create proposal evaluation worksheets
Databases: track suppliers
Presentation software: present procurement-related information
E-procurement software: electronic procurement functions

## Slide 27: Using Software to Assist in Project Procurement Management (2 of 2)
Procure-to-pay suite: provides support for indirect procurements
  E-purchasing functionality
  Catalog management capabilities
  E-invoicing
  Accounts Payable Invoice Automation

## Slide 28: Considerations for Agile/Adaptive Environments
Agile Manifesto values customer collaboration over contract negotiation, setting an important tone for procurement relationships on agile projects
  The buyer and seller should work together to create the required products and services throughout the entire procurement process
Another goal of agile/adaptive environments is speed
  Several procurements, however, take time
Processes of project procurement management follow a clear, logical sequence
  Project managers and their teams must follow good project procurement management

## Slide 29: Chapter Summary
Procurement, purchasing, or outsourcing is the acquisition of goods and services from an outside source
  Project procurement management includes planning procurement management and then conducting and controlling procurements
    Involves deciding what to procure or outsource, what type of contract to use, and how to describe the effort in a statement of work
  Several types of software can assist in project procurement management